## Calendar
MEAL calendar | 2019 - 2021 |  |  | planned |  | done |  | canceled
Coutry: | Update 10.04.2019
MEAL activities | 2019 |  |  |  | 2020 |  |  |  | 2021
| 1st Qrt | 2nd Qrt | 3rd. Qrt | 4th Qrt | 1st Qrt | 2nd Qrt | 3rd. Qrt | 4th Qrt | 1st Qrt | 2nd Qrt | 3rd. Qrt | 4th Qrt
Project number….
Baseline survey |  | 2015-04-01
Midterm evaluation (intern)
Endline survey
Final evaluation (evaluator(s)) | [6 empty] | 2010-06-01
MAPP evaluation
Learning event | [6 empty] | Review meeting
CRM |  | prepartion meeting
Feedback mechanisms loops
…..
Project number….
Feasability study survey
Baseline survey
Midterm evaluation | [6 empty] | 2013-07-01
Endline survey
Programme review
CRM
Information sharing activities
…
Project number…

## How to use
How to use the MEAL calendar
Purpose: The Meal calendar is provinding an overview about all essential MEAL dates and appointments of a project or also of all running projects over a period of 1 to 3 years for a good planning.
Handling: Project-related activities concerning MEAL can be listed in first left-hand column with title "MEAL activities". For example, project baseline surveys, midterm evaluations, MAPP evaluations, accountability activities like CRM, learning events and others. The selected date for the activities can be entered in the column for the respective year, with use of a certain colour code to determine status of the scheduled activity. The calendar shall be updated on a regular basis, for example, in regular project or programme meetings. People responsible for maintenance and follow up of the MEAL calendar can be MEAL experts, but also staff with responsibility in MEAL.
Adapatation: The MEAL calendar is easy to use and modify, even with only a little knowledge of Excel. Colours for status can be adjusted or extented. There is no limit of projects or activities. All columns and grids can be extended.
Support: If questions in handling the tool or use for effective planning arise, please contact your Head Office MEAL advisor.